CHAPTER 11

Project Management

Teaching Suggestions

Teaching Suggestion 11.1: Importance of PERT.

PERT has rebounded and, due to PC software such as Microsoft Project, become a highly used quantitative analysis technique. It can be useful for organizations of all sizes and any individuals involved in planning and controlling projects. A good way to start this chapter is to discuss the capabilities of PERT. Students can be asked to contact a local firm (such as a builder) to ask about the use of PERT.

Teaching Suggestion 11.2: Getting Students Involved with PERT.

PERT is a technique that students can apply immediately. For example, students can be asked to use PERT to plan the courses they will need to take and the timing of taking these courses until graduation. Another approach would be to have students take a typical semester and use PERT to plan the term papers, exams, and assignments that must be finished to successfully complete the semester.

Teaching Suggestion 11.3: Constructing a Network.

One of the most difficult tasks of PERT or CPM is to develop an accurate network that reflects the true situation. Students should be given practice in this important aspect of network analysis as early as possible. Use the end-of-chapter problems. Students can be asked to develop their own networks. We can’t stress enough the importance of drawing networks, since many students have a conceptual problem with the task.

Teaching Suggestion 11.4: Using the Beta Distribution.

PERT uses the beta distribution in estimating expected times and variances for each activity. As a matter of fact, it is questionable whether the beta distribution is appropriate. Students should be told that other distributions such as the normal curve can be used. A discrete probability distribution can also be used to determine expected times and variances. Instead of using optimistic, most likely, and pessimistic time estimates, an entire discrete distribution can be used to determine expected times and variances.

Teaching Suggestion 11.5: Finding the Critical Path.

Finding the critical path is not too difficult if the steps given in this chapter are followed. Students should be reminded that in making the forward pass all predecessor activities must be completed before any activity can be started. In the backward pass, students should be reminded that latest time is computed by making sure that the project would not be delayed for any activity. This means that all activities must be completed within the original project completion time.

Teaching Suggestion 11.6: Project Crashing.

In manually performing project crashing, the critical path may change. In many cases, two or more critical paths will exist after crashing. Students should be reminded of this problem. Fortunately, the linear programming approach or the use of PERT software, including QM for Windows, automatically takes care of this potential problem.

Alternative Examples

Alternative Example 11.1:  Sid Orland is involved in planning a scientific research project. The activities are displayed in the following diagram. Optimistic, most likely, and pessimistic time estimates are displayed in the following table.

Figure for Alternative Example 11.1

|  |  | Most |  |
| --- | --- | --- | --- |
| Activity | Optimistic | Likely | Pessimistic |
| A | 3 | 4 | 5 |
| B | 3 | 3 | 3 |
| C | 2 | 3 | 4 |
| D | 1 | 3 | 5 |
| E | 4 | 4 | 4 |
| F | 2 | 2 | 2 |
| G | 4 | 5 | 6 |
| H | 3 | 4 | 5 |

The activities along the critical path and the total project completion times are shown in the figure. The solution is shown. As can be seen, the total project completion time is 20 weeks. Critical path activities are A, C, E, G, and H.

| Activity | Mean | S.D. | Variance |
| --- | --- | --- | --- |
| A* | 4 | 0.333 | 0.111 |
| B | 3 | 0.000 | 0.000 |
| C* | 3 | 0.333 | 0.111 |
| D | 3 | 0.667 | 0.444 |
| E* | 4 | 0.000 | 0.000 |
| F | 2 | 0.000 | 0.000 |
| G* | 5 | 0.333 | 0.111 |
| H* | 4 | 0.333 | 0.111 |

*Critical Path Activities

Expected Completion Time: 20

Alternative Example 11.2:  Sid Orland would like to reduce the project completion time for the problem in Alternative Example 11-1 by 2 weeks. The normal and crash times and costs are presented in the table.

|  |  | Time |  | Cost |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Immediate Predecessor | Normal | Crash | Normal | Crash |
| A | — | 4 | 3 | $2,000 | $3,000 |
| B | — | 3 | 3 | 3,000 | 3,000 |
| C | A | 3 | 2 | 5,000 | 6,000 |
| D | B | 3 | 2 | 5,000 | 5,500 |
| E | C | 4 | 3 | 8,000 | 10,000 |
| F | C | 2 | 2 | 2,000 | 2,000 |
| G | D,E | 5 | 3 | 3,000 | 4,000 |
| H | F,G | 4 | 4 | 4,000 | 4,000 |

From the table, the crash cost per week can be determined for each activity. This information is displayed in the following table.

| Activity | Critical Path? | Crash Cost per Week |
| --- | --- | --- |
| A | Yes | $1,000 |
| B |  | 0 or NA |
| C | Yes | $1,000 |
| D |  | $500 |
| E | Yes | $2,000 |
| F |  | 0 or NA |
| G | Yes | $500 |
| H | Yes | 0 or NA |

Given this information, the least expensive way to reduce the project using an activity on the critical path is to reduce activity G by 2 weeks, for a total cost of $1,000 ($1,000 = 2  $500).

Solutions to Discussion Questions and Problems

11-1.  PERT and CPM can answer a number of questions about a project or the activities within a project. These techniques can determine the earliest start, earliest finish, latest start, and the latest finish times for all activities within a network. Furthermore, these techniques can be used to determine the project completion data for the entire project, the slack for all activities, and those activities that are along the critical path of the network.

11-2.  There are several major differences between PERT and CPM. With PERT, three estimates of activity time and completion are made. These are the optimistic, most likely, and pessimistic time estimates. From these estimates, the expected completion time and completion variance can be determined. CPM allows the use of crashing. This technique allows a manager to reduce the total project completion time by expending additional resources on activities within the network. CPM is used in determining the least-cost method of crashing a project or network.

11-3.  An activity is a task that requires a fixed amount of time and resources to complete. An event is a point in time. Events mark the beginning and ending of activities. An immediate predecessor is an activity that must be completely finished before another activity can be started.

11-4.  Expected activity times and variances can be computed by making the assumption that activity times follow a beta distribution. Three time estimates are used to determine the expected activity time and variance for each activity.

11-5.  The critical path consists of those activities that will cause a delay in the entire project if they themselves are delayed. These critical path activities have zero slack. If they are delayed, the entire project is delayed. Critical path analysis is a way of determining the activities along the critical path and the earliest start time, earliest finish time, latest start time, and the latest finish time for every activity. It is important to identify these activities because if they are delayed, the entire project will be delayed.

11-6.  The earliest activity start time is the earliest time that an activity can be started while all predecessor activities are completely finished. The earliest activity start times are determined using a forward pass through the network. The latest activity start time represents the latest time that an activity can be started without delaying the entire project. Latest activity start times are determined by making a backward pass through the network.

11-7.  Slack is the amount of time that an activity can be delayed without delaying the entire project. If the slack is zero, the activity cannot be delayed at all without delaying the entire project. For any activity, slack can be determined by subtracting the earliest start from the latest start time, or by subtracting the earliest finish from the latest finish time.

11-8.  We can determine the probability that a project will be completed by a certain date by knowing the expected project completion time and variance. The expected project completion time can be determined by adding the activity times for those activities along the critical path. The total project variance can be determined by adding the variance of those activities along the critical path. In most cases, we make the assumption that the project completion times follow a normal distribution. When this is done, we can use a standard normal table in computing the probability that a project will be completed by a certain date.

11-9.  PERT/Cost is used to monitor and control project cost in addition to the time it takes to complete a particular project. This can be done by making a budget for the entire project using the activity cost estimates and by monitoring the budget as the project takes place. Using this approach we can determine the extent to which a project is incurring a cost overrun or a cost underrun. In addition, we can use the same technique to determine the extent to which a project is ahead of schedule or behind schedule.

11-10.  Crashing is the process of reducing the total time it takes to complete a project by expending additional resources. In performing crashing by hand, it is necessary to identify those activities along the critical path and then to reduce those activities which cost the least to reduce or crash. This is continued until the project is crashed to the desired completion date. In doing this, however, two or more critical paths can develop in the same network.

11-11.  Linear programming is very useful in CPM crashing because it is a commonly used technique and many computer programs exist that can easily be used to crash a network. In addition, there are many sensitivity and ranging techniques that are available with linear programming.

11-12.

11-13. <NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

| <NOXMLTAGINDOC><DOCPAGE NUM="191"></DOCPAGE></NOXMLTAGINDOC> |  |  |  |  |  | Critical |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | ES | EF | LS | LF | Stack | Activity |
| A | 0 | 2 | 13 | 15 | 13 | No |
| B | 0 | 5 | 0 | 5 | 0 | Yes |
| C | 0 | 1 | 11 | 12 | 11 | No |
| D | 5 | 15 | 5 | 15 | 0 | Yes |
| E | 15 | 18 | 15 | 18 | 0 | Yes |
| F | 1 | 7 | 12 | 18 | 11 | No |
| G | 18 | 26 | 18 | 26 | 0 | Yes |

The critical path is B–D–E–G. Project completion time is 26 days.

11-14.

11-15.

The critical path is B–D–E–G. Project completion time is 17 days.

11-16.

11-17.<NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

|  | Time |  |  |  |  |  | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | (Weeks) | ES | EF | LS | LF | S | Activity |
| A | 6 | 0 | 6 | 0 | 6 | 0 | Yes |
| B | 5 | 0 | 5 | 0 | 5 | 0 | Yes |
| C | 3 | 6 | 9 | 6 | 9 | 0 | Yes |
| D | 2 | 6 | 8 | 10 | 12 | 4 | No |
| E | 4 | 5 | 9 | 5 | 9 | 0 | Yes |
| F | 6 | 5 | 11 | 6 | 12 | 1 | No |
| G | 10 | 9 | 19 | 9 | 19 | 0 | Yes |
| H | 7 | 11 | 18 | 12 | 19 | 1 | No |

There are two critical paths: A–C–G and B–E–G. Project completion time is 19 weeks.

11-18.   = 40, 2 = 9,  = 3

a.   <ART FILE="13_18eq01.EPS" W="174.769pt" H="20.308pt" XS="100%" YS="100%"/>

b. <ART FILE="13_18eq02.EPS" W="149.077pt" H="30.656pt" XS="100%" YS="100%"/>

c. <ART FILE="13_18eq03.EPS" W="181.538pt" H="20.308pt" XS="100%" YS="100%"/>

d. P(X  46) = P(Z  2) = 1 – 0.97725 = 0.02275

e. P(X  Due Date) = 0.90 For a probability of 0.90, z = 1.28.

<ART FILE="13_18eq04.EPS" W="52.923pt" H="20.264pt" XS="100%" YS="100%"/>

X = 40 + 1.28(3) = 43.84.

Thus, the due date should be 43.84 weeks

11-19. <NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

| <NOXMLTAGINDOC><DOCPAGE NUM="193"></DOCPAGE></NOXMLTAGINDOC>Activity | a | m | b | t | V | ES | EF | LS | LF | S |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 8 | 10 | 12 | 10.0 | 0.44 | 0 | 10.0 | 0 | 10.0 | 0 |
| B | 6 | 7 | 9 | 7.2 | 0.25 | 0 | 7.2 | 22.8 | 30.0 | 22.3 |
| C | 3 | 3 | 4 | 3.2 | 0.03 | 0 | 3.2 | 19.8 | 23.0 | 19.8 |
| D | 10 | 20 | 30 | 20.0 | 11.11 | 10.0 | 30.0 | 10.0 | 30.0 | 0 |
| E | 6 | 7 | 8 | 7.0 | 0.11 | 3.2 | 10.2 | 23.0 | 30.0 | 19.8 |
| F | 9 | 10 | 11 | 10.0 | 0.11 | 30.0 | 40.0 | 30.0 | 40.0 | 0 |
| G | 6 | 7 | 10 | 7.3 | 0.44 | 30.0 | 37.3 | 47.7 | 55.0 | 17.7 |
| H | 14 | 15 | 16 | 15.0 | 0.11 | 40.0 | 55.0 | 40.0 | 55.0 | 0 |
| I | 10 | 11 | 13 | 11.2 | 0.25 | 40.0 | 51.2 | 50.8 | 62.0 | 10.8 |
| J | 6 | 7 | 8 | 7.0 | 0.11 | 55.0 | 62.0 | 55.0 | 62.0 | 0 |
| K | 4 | 7 | 8 | 6.7 | 0.44 | 62.0 | 68.7 | 62.0 | 68.7 | 0 |
| L | 1 | 2 | 4 | 2.2 | 0.25 | 55.0 | 57.2 | 66.5 | 68.7 | 11.5 |

The critical path is A–D–F–H–J–K. Project completion time is 68.7 days. Project variance is 0.44 + 11.11 + 0.11 + 0.11 + 0.11 + 0.44 = 12.32.

<ART FILE="13_19eq01.EPS" W="64.75pt" H="13.25pt" XS="100%" YS="100%"/>

<ART FILE="13_19eq02.EPS" W="38.47pt" H="9.778pt" XS="100%" YS="100%"/>

<ART FILE="13_19eq03.EPS" W="182.238pt" H="25.524pt" XS="100%" YS="100%"/>

<ART FILE="13_19eq04.EPS" W="182.238pt" H="25.524pt" XS="100%" YS="100%"/>

<ART FILE="13_19eq05.EPS" W="184.238pt" H="25.524pt" XS="100%" YS="100%"/>

11-20.  Assuming normal distribution for project completion time:

a.	<ART FILE="13_20eq01.EPS" W="172.444pt" H="38.618pt" XS="100%" YS="100%"/>

b.	<ART FILE="13_20eq02.EPS" W="173.581pt" H="38.667pt" XS="100%" YS="100%"/>

c.	<ART FILE="13_20eq03.EPS" W="140pt" H="27.278pt" XS="100%" YS="100%"/>

d.	<ART FILE="13_20eq04.EPS" W="139.556pt" H="27pt" XS="100%" YS="100%"/>

11-21.

|  | Total |  | Value of |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Budgeted | Percentage of | Work | Actual | Activity |
| Activity | Cost | Completion | Completed | Cost | Difference |
| A | $22,000 | 100 | $22,000 | $20,000 | –$2,000 |
| B | 30,000 | 100 | 30,000 | 36,000 | 6,000 |
| C | 26,000 | 100 | 26,000 | 26,000 | 0 |
| D | 48,000 | 100 | 48,000 | 44,000 | –4,000 |
| E | 56,000 | 50 | 28,000 | 25,000 | –3,000 |
| F | 30,000 | 60 | 18,000 | 15,000 | –3,000 |
| G | 80,000 | 10 | 8,000 | 5,000 | –3,000 |
| H | 16,000 | 10 | 1,600 | 1,000 | –600 |

After 8 weeks:

Value of work completed = $181,600

Actual cost = $172,000

Cost underrun = $9,600

Using Table 11.6, $212,000 should have been spent using ES times. Using Table 11.7, with LS times, $182,000 should have been spent. Hence the project is behind schedule but there is a cost underrun on the whole.

11-22.

|  |  |  |  | Total | Cost |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Cost | Per |
| Activity | ES | LS | t | ($1,000 s) | Month |
| A | 0 | 0 | 6 | 10 | $1,667 |
| B | 1 | 4 | 2 | 14 | 7,000 |
| C | 3 | 3 | 7 | 5 | 714 |
| D | 4 | 9 | 3 | 6 | 2,000 |
| E | 6 | 6 | 10 | 14 | 1,400 |
| F | 14 | 15 | 11 | 13 | 1,182 |
| G | 12 | 18 | 2 | 4 | 2,000 |
| H | 14 | 14 | 11 | 6 | 545 |
| I | 18 | 21 | 6 | 18 | 3,000 |
| J | 18 | 19 | 4 | 12 | 3,000 |
| K | 22 | 22 | 14 | 10 | 714 |
| L | 22 | 23 | 8 | 16 | 2,000 |
| M | 18 | 24 | 6 | 118 | 3,000 |
|  |  |  |  | 146 |  |

Using earliest starting times.

11-22.	a.	Monthly budget using earliest starting times:

| <NOXMLTAGINDOC><DOCPAGE NUM="195"></DOCPAGE></NOXMLTAGINDOC> | Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month | A | B | C | D | E | F | G | H | I | J | K | L | M | Total |
| 1 | 1667 |  |  |  |  |  |  |  |  |  |  |  |  | 1667 |
| 2 | 1667 | 7000 |  |  |  |  |  |  |  |  |  |  |  | 8667 |
| 3 | 1667 | 7000 |  |  |  |  |  |  |  |  |  |  |  | 8667 |
| 4 | 1667 |  | 714 |  |  |  |  |  |  |  |  |  |  | 2381 |
| 5 | 1667 |  | 714 | 2000 |  |  |  |  |  |  |  |  |  | 4381 |
| 6 | 1667 |  | 714 | 2000 |  |  |  |  |  |  |  |  |  | 4381 |
| 7 |  |  | 714 | 2000 | 1400 |  |  |  |  |  |  |  |  | 4114 |
| 8 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 9 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 10 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 11 |  |  |  |  | 1400 |  |  |  |  |  |  |  |  | 1400 |
| 12 |  |  |  |  | 1400 |  |  |  |  |  |  |  |  | 1400 |
| 13 |  |  |  |  | 1400 |  | 2000 |  |  |  |  |  |  | 3400 |
| 14 |  |  |  |  | 1400 |  | 2000 |  |  |  |  |  |  | 3400 |
| 15 |  |  |  |  | 1400 | 1182 |  | 545 |  |  |  |  |  | 3127 |
| 16 |  |  |  |  | 1400 | 1182 |  | 545 |  |  |  |  |  | 3127 |
| 17 |  |  |  |  |  | 1182 |  | 545 |  |  |  |  |  | 1727 |
| 18 |  |  |  |  |  | 1182 |  | 545 |  |  |  |  |  | 1727 |
| 19 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 |  |  | 3000 | 10727 |
| 20 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 |  |  | 3000 | 10727 |
| 21 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 |  |  | 3000 | 10727 |
| 22 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 |  |  | 3000 | 10727 |
| 23 |  |  |  |  |  | 1182 |  | 545 | 3000 |  | 714 | 2000 | 3000 | 10442 |
| 24 |  |  |  |  |  | 1182 |  | 545 | 3000 |  | 714 | 2000 | 3000 | 10442 |
| 25 |  |  |  |  |  | 1182 |  | 545 |  |  | 714 | 2000 |  | 4442 |
| 26 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 27 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 28 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 29 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 30 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 31 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 32 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 33 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 34 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 35 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 36 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| Total | 10000 | 14000 | 5000 | 6000 | 14000 | 13000 | 4000 | 6000 | 18000 | 12000 | 10000 | 16000 | 18000 | 146000 |

- Monthly budget using latest starting times:

|  | Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month | A | B | C | D | E | F | G | H | I | J | K | L | M | Total |
| 1 | 1667 |  |  |  |  |  |  |  |  |  |  |  |  | 1667 |
| 2 | 1667 |  |  |  |  |  |  |  |  |  |  |  |  | 1667 |
| 3 | 1667 |  |  |  |  |  |  |  |  |  |  |  |  | 1667 |
| 4 | 1667 |  | 714 |  |  |  |  |  |  |  |  |  |  | 2381 |
| 5 | 1667 | 7000 | 714 |  |  |  |  |  |  |  |  |  |  | 9381 |
| 6 | 1667 | 7000 | 714 |  |  |  |  |  |  |  |  |  |  | 9381 |
| 7 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 8 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 9 |  |  | 714 |  | 1400 |  |  |  |  |  |  |  |  | 2114 |
| 10 |  |  | 714 | 2000 | 1400 |  |  |  |  |  |  |  |  | 4114 |
| 11 |  |  |  | 2000 | 1400 |  |  |  |  |  |  |  |  | 3400 |
| 12 |  |  |  | 2000 | 1400 |  |  |  |  |  |  |  |  | 3400 |
| 13 |  |  |  |  | 1400 |  |  |  |  |  |  |  |  | 1400 |
| 14 |  |  |  |  | 1400 |  |  |  |  |  |  |  |  | 1400 |
| 15 |  |  |  |  | 1400 |  |  | 545 |  |  |  |  |  | 1945 |
| 16 |  |  |  |  | 1400 | 1182 |  | 545 |  |  |  |  |  | 3127 |
| 17 |  |  |  |  |  | 1182 |  | 545 |  |  |  |  |  | 1727 |
| 18 |  |  |  |  |  | 1182 |  | 545 |  |  |  |  |  | 1727 |
| 19 |  |  |  |  |  | 1182 | 2000 | 545 |  |  |  |  |  | 3727 |
| 20 |  |  |  |  |  | 1182 | 2000 | 545 |  | 3000 |  |  |  | 6727 |
| 21 |  |  |  |  |  | 1182 |  | 545 |  | 3000 |  |  |  | 4727 |
| 22 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 |  |  |  | 7727 |
| 23 |  |  |  |  |  | 1182 |  | 545 | 3000 | 3000 | 714 |  |  | 8442 |
| 24 |  |  |  |  |  | 1182 |  | 545 | 3000 |  | 714 | 2000 |  | 7442 |
| 25 |  |  |  |  |  | 1182 |  | 545 | 3000 |  | 714 | 2000 | 3000 | 10442 |
| 26 |  |  |  |  |  | 1182 |  |  | 3000 |  | 714 | 2000 | 3000 | 9896 |
| 27 |  |  |  |  |  |  |  |  | 3000 |  | 714 | 2000 | 3000 | 8714 |
| 28 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 | 3000 | 5714 |
| 29 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 | 3000 | 5714 |
| 30 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 | 3000 | 5714 |
| 31 |  |  |  |  |  |  |  |  |  |  | 714 | 2000 |  | 2714 |
| 32 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 33 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 34 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 35 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| 36 |  |  |  |  |  |  |  |  |  |  | 714 |  |  | 714 |
| Total | 10000 | 14000 | 5000 | 6000 | 14000 | 13000 | 4000 | 6000 | 18000 | 12000 | 10000 | 16000 | 18000 | 146000 |

11-23.

The critical path is A–C–E–G–H. Total time is 15 weeks.

1.  Activities A, C, and E all have minimum crash costs per week of $1,000.

2.  Reduce activity E by 1 week for a total cost of $1,000. There are now two critical paths.

3.  The total project completion time is now 14 weeks and the new critical paths are B–D–G–H and A–C–E–G–H.

4.  Activities D and E have minimum crashing costs per week for each critical path.

5.  Reduce activities D and E by 1 week each for a total cost of $3,000, including the reduction of E by 1 week.

6.  The total project completion time is 13 weeks. There are two critical paths: A–C–E–G–H and B–D–G–H.

11-24.<NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="189"> <ART FILE="UN13_001_0136036287.EPS" W="360pt" H="144pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

|  |  |  |  |  | Crash Cost |
| --- | --- | --- | --- | --- | --- |
| Activity | Normal time | Crash time | Normal cost | Crash cost | per Week |
| A | 3 | 2 | 1,000 | 1,600 | $ 600 |
| B | 2 | 1 | 2,000 | 2,700 | 700 |
| C | 1 | 1 | 300 | 300 | 0 |
| D | 7 | 3 | 1,300 | 1,600 | 75 |
| E | 6 | 3 | 850 | 1,000 | 50 |
| F | 2 | 1 | 4,000 | 5,000 | 1,000 |
| G | 4 | 2 | 1,500 | 2,000 | 250 |

Project completion time is 14. This project has to be crashed to 10. This is done by the following linear programming formulation:

If Xi is the start time for activity i where i = C, D, E, F, G, and Finish, and Yj is the amount of time reduced for activity j, where j = A, B, C, D, E, F, G.

Minimize Z = 600YA + 700YB + 0YC + 75YD

+ 50YE + 1,000YF + 250YG

subject to

YA	 1

YB	 1

YC	 0

YD	 4

YE	 3

YF	 1

YG	 2

XFinish	 10

XFinish – XG + YG  4	XD – XA + YA  3

XG – XE + YE  6	XFinish – XF + YF  2

XG – XD + YD  7	XF – XC + YC  1

XE – XB + YB  2	          All Xi, Yj  0

11-25.  The Bender Construction Co. problem is one involving 23 separate activities. These activities, their immediate predecessors, and time estimates were given in the problem. The first results of the computer program are the expected time and variance estimates for each activity.

These data are shown in the following table.

| <NOXMLTAGINDOC><DOCPAGE NUM="197"></DOCPAGE></NOXMLTAGINDOC>Activity | Time | Variance |
| --- | --- | --- |
| 1 | 3.67 | 0.444 |
| 2 | 3.00 | 0.111 |
| 3 | 4.00 | 0.111 |
| 4 | 8.00 | 0.111 |
| 5 | 4.17 | 0.028 |
| 6 | 2.17 | 0.250 |
| 7 | 5.00 | 0.111 |
| 8 | 2.17 | 0.250 |
| 9 | 3.83 | 0.028 |
| 10 | 1.17 | 0.028 |
| 11 | 20.67 | 1.778 |
| 12 | 2.00 | 0.111 |
| 13 | 1.17 | 0.028 |
| 14 | 0.14 | 0.000 |
| 15 | 0.30 | 0.001 |
| 16 | 1.17 | 0.028 |
| 17 | 2.00 | 0.111 |
| 18 | 5.00 | 0.444 |
| 19 | 0.12 | 0.000 |
| 20 | 0.14 | 0.000 |
| 21 | 3.33 | 0.444 |
| 22 | 0.12 | 0.000 |
| 23 | 0.17 | 0.001 |

Next, the computer determines the expected project length, variance, and data for all activities. Like the other network problems, these data include the earliest start, earliest finish, latest start, latest finish, and slack times for all activities. The data are shown in the following table.

|  | Activity Time |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity |  |  |  |  |  |
| S–F | ES | EF | LS | LF | Slack |
| 1 | 0.00 | 3.67 | 9.00 | 12.67 | 9.00 |
| 2 | 0.00 | 3.00 | 16.50 | 19.50 | 16.50 |
| 3 | 0.00 | 4.00 | 14.50 | 18.50 | 14.50 |
| 4 | 0.00 | 8.00 | 3.50 | 11.50 | 3.50 |
| 5 | 3.67 | 7.83 | 12.67 | 16.83 | 9.00 |
| 6 | 4.00 | 6.17 | 18.50 | 20.67 | 14.50 |
| 7 | 8.00 | 13.00 | 11.50 | 16.50 | 3.50 |
| 8 | 13.00 | 15.17 | 16.50 | 18.67 | 3.50 |
| 9 | 7.83 | 11.67 | 16.83 | 20.67 | 9.00 |
| 10 | 3.00 | 4.17 | 19.50 | 20.67 | 16.50 |
| 11 | 0.00 | 20.67 | 0.00 | 20.67 | 0.00* |
| 12 | 15.17 | 17.17 | 18.67 | 20.67 | 3.50 |
| 13 | 20.67 | 21.83 | 20.67 | 21.83 | 0.00* |
| 14 | 21.83 | 21.97 | 21.83 | 21.97 | 0.00* |
| 15 | 21.97 | 22.27 | 24.84 | 25.14 | 2.87 |
| 16 | 21.97 | 23.14 | 21.97 | 23.14 | 0.00* |
| 17 | 23.14 | 25.14 | 23.14 | 25.14 | 0.00* |
| 18 | 25.14 | 30.14 | 25.14 | 30.14 | 0.00* |
| 19 | 30.14 | 30.25 | 30.14 | 30.25 | 0.00* |
| 20 | 30.25 | 30.39 | 33.33 | 33.47 | 3.08 |
| 21 | 30.25 | 33.59 | 30.25 | 33.59 | 0.00* |
| 22 | 30.39 | 30.51 | 33.47 | 33.59 | 3.08 |
| 23 | 33.59 | 33.77 | 33.59 | 33.77 | 0.00* |

*Indicates critical path activity.

As you can see, the expected project length is about 34 weeks. The activities along the critical path are activities 11, 13, 14, 16, 17, 18, 19, 21, and 23.

Figure for Problem 11-25: Activities for Bender Constructions<NOXMLTAGINDOC> <DOCPAGE NUM="198"> <ART FILE="UN13_011_0136036287.EPS" W="504pt" H="84.59pt" XS="100%" YS="99.998%"/> </DOCPAGE> </NOXMLTAGINDOC>

11-26.  The overall purpose of Problem 11-26 is to have students use a network approach in attempting to solve a problem that almost all students face. The first step is for students to list all courses that they must take, including possible electives, to get a degree from their particular college or university. For every course, students should list all the immediate predecessors. Then students are asked to attempt to develop a network diagram that shows these courses and their immediate predecessors or prerequisite courses.

This problem can also point out some of the limitations of the use of PERT. As students try to solve this problem using the PERT approach, they may run into several difficulties. First, it is difficult to incorporate a minimum or maximum number of courses that a student can take during a given semester. In addition, it is difficult to schedule elective courses. Some elective courses have prerequisites, while others may not. Some courses may not be offered every semester.  Even so, some of the overall approaches of network analysis can be helpful in terms of laying out the courses that are required and their prerequisites.

Students can also be asked to think about other quantitative techniques that can be used in solving this problem. One of the most appropriate approaches would be to use linear programming to incorporate many of the constraints, such as minimum and maximum number of credit hours per semester, that are difficult or impossible to incorporate in a PERT network.

11-27.  a.  This project management problem can be solved using the PERT model discussed in the chapter.

Task time computations

|  | Optimistic | Most | Pessimistic | Activity | Activity |
| --- | --- | --- | --- | --- | --- |
|  | Time | Likely Time | Time | Time | Variance |
| Task 1 | 1 | 2 | 4 | 2.1667 | 2.1667 |
| Task 2 | 3 | 3.5 | 4 | 3.5 | 3.5 |
| Task 3 | 10 | 12 | 13 | 11.8333 | 11.8333 |
| Task 4 | 4 | 5 | 7 | 5.1667 | 5.1667 |
| Task 5 | 2 | 4 | 5 | 3.8333 | 3.8333 |
| Task 6 | 6 | 7 | 8 | 7 | 7 |
| Task 7 | 2 | 4 | 5.5 | 3.9167 | 3.9167 |
| Task 8 | 5 | 7.7 | 9 | 7.4667 | 7.4667 |
| Task 9 | 9.9 | 10 | 12 | 10.3167 | 10.3167 |
| Task 10 | 2 | 4 | 5 | 3.8333 | 3.8333 |
| Task 11 | 2 | 4 | 6 | 4 | 4 |
| Task 12 | 2 | 4 | 6 | 4 | 4 |
| Task 13 | 5 | 6 | 6.5 | 5.9167 | 5.9167 |
| Task 14 | 1 | 1.1 | 2 | 1.2333 | 1.2333 |
| Task 15 | 5 | 7 | 8 | 6.8333 | 6.8333 |
| Task 16 | 5 | 7 | 9 | 7 | 7 |

The results are in the table. As you can see, the total project completion time is about 32 weeks. The critical path consists of Tasks 3, 8, 13, and 15.

| Activity | Activity time | Early Start | Early Finish | Latest Start | Latest Finish | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| Task 1 | 2.17 | 0 | 2.17 | 10.13 | 12.3 | 10.13 |
| Task 2 | 3.5 | 0 | 3.5 | 11.88 | 15.38 | 11.88 |
| Task 3 | 11.83 | 0 | 11.83 | 0 | 11.83 | 0 |
| Task 4 | 5.17 | 0 | 5.17 | 14.65 | 19.82 | 14.65 |
| Task 5 | 3.83 | 0 | 3.83 | 15.98 | 19.82 | 15.98 |
| Task 6 | 7 | 2.17 | 9.17 | 12.3 | 19.3 | 10.13 |
| Task 7 | 3.92 | 3.5 | 7.42 | 15.38 | 19.3 | 11.88 |
| Task 8 | 7.47 | 11.83 | 19.3 | 11.83 | 19.3 | 0 |
| Task 9 | 10.32 | 11.83 | 22.15 | 14.9 | 25.22 | 3.07 |
| Task 10 | 3.83 | 11.83 | 15.67 | 19.98 | 23.82 | 8.15 |
| Task 11 | 4 | 5.17 | 9.17 | 19.82 | 23.82 | 14.65 |
| Task 12 | 4 | 3.83 | 7.83 | 19.82 | 23.82 | 15.98 |
| Task 13 | 5.92 | 19.3 | 25.22 | 19.3 | 25.22 | 0 |
| Task 14 | 1.23 | 15.67 | 16.9 | 23.82 | 25.05 | 8.15 |
| Task 15 | 6.83 | 25.22 | 32.05 | 25.22 | 32.05 | 0 |
| Task 16 | 7 | 16.9 | 23.9 | 25.05 | 32.05 | 8.15 |

<NOXMLTAGINDOC><DOCPAGE NUM="199"></DOCPAGE></NOXMLTAGINDOC>Project completion time = 32.05

Project standard deviation = 1.003466

b.  If  Task 9 and 10 were not necessary, a time of 0 could be given for each and the critical path could be found again.  However, these changes do not have any impact on the critical path or the total project completion time.

11-28.  a.

| Activity | a | m | b | t | 2 |
| --- | --- | --- | --- | --- | --- |
| A | 9 | 10 | 11 | 10 | 0.111 |
| B | 4 | 10 | 16 | 10 | 4 |
| C | 9 | 10 | 11 | 10 | 0.111 |
| D | 5 | 8 | 11 | 8 | 1 |

b.  The critical path is AC with an expected completion time of 20. The expected completion time of BD is 18.

c.  The variance of AC = 0.111 + 0.111 = 0.222. The variance of BD = 4 + 1 = 5.

d.

<ART FILE="13_28eq01.EPS" W="220.8pt" H="33.6pt" XS="100%" YS="100%"/>

e.

<ART FILE="13_28eq02.EPS" W="229.2pt" H="27.2pt" XS="100%" YS="100%"/>

f.  The path BD has a very large variance. Thus, it is likely that it will take much longer than its expected time. Therefore, while it is almost certain that the critical path (AC) will be finished in 22 weeks or less, there is only a 96% chance the other path (BD) will be finished in that time.

<NOXMLTAGINDOC><DOCPAGE NUM="201"></DOCPAGE></NOXMLTAGINDOC>11-29  a.

Budget schedule based on earliest times. Costs are in $1,000s

|  | Week |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| A |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |
| B |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |
| Total in Period |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 2 | 2 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2 | 2 |
| Cumulative from start |  | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 37 | 39 | 41 | 44.5 | 48 | 51.5 | 55 | 58.5 | 62 | 64 | 66 |

b.  Budget schedule based on latest times. Costs are in $1,000s.

|  | Week |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |
| F |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |
| Total in Period | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 2 | 2 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |
| Cumulative from start | 1 | 2 | 6 | 10 | 14 | 18 | 22 | 26 | 31 | 36 | 41 | 43 | 45 | 48.5 | 52 | 55.5 | 59 | 62.5 | 66 |

c.  Budget schedule based on earliest times. Costs are in $1,000s.

|  | Week |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |
| B | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |
| D |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 | 1 | 1 |
| Total in Period | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 2 | 2 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 5.5 | 1 | 1 |
| Cumulative from start | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 37 | 39 | 41 | 44.5 | 48 | 51.5 | 55 | 58.5 | 64 | 65 | 66 |

11-30.  The total time to complete the project is 17 weeks. The critical path is A-E-G-H.

11-31.  a. Crash G 1 week at an additional cost of $700.

b. The paths are A-E-G-H, A-C-F-H, and B-D-G-H. When G is crashed 1 week so the project time is 16 weeks, there are two critical paths A-E-G-H and A-C-F-H. Each of these paths must have their times reduced by one week. The least cost way to do this is to crash H (which is on both paths) I week for an additional cost of $800.

11-32.

|  | Time |  |  |  |  |  | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | (Weeks) | ES | EF | LS | LF | S | Activity |
| A | 4 | 0 | 4 | 8 | 12 | 8 | No |
| B | 8 | 0 | 8 | 0 | 8 | 0 | Yes |
| C | 5 | 4 | 9 | 14 | 19 | 10 | No |
| D | 11 | 8 | 19 | 8 | 19 | 0 | Yes |
| E | 7 | 8 | 15 | 12 | 19 | 4 | No |
| F | 10 | 15 | 25 | 19 | 29 | 4 | No |
| G | 16 | 19 | 35 | 19 | 35 | 0 | Yes |
| H | 6 | 25 | 31 | 29 | 35 | 4 | No |

This can be formulated as a linear programming, similar to the one used for crashing.  Let XA = earliest finish time for activity A

XB = earliest finish time for activity B

XC  = earliest finish time for activity C

XD  = earliest finish time for activity D

XE = earliest finish time for activity E

XF = earliest finish time for activity F

XG = earliest finish time for activity G

XH = earliest finish time for activity H

Minimize  XH

Subject to

XA  > 4

XB  > 8

XC  > 5 + XA

XD  > 11 + XB

XE  > 7 + XA

XE  > 7 + XB

XF  > 10 + XC

XF  > 10 + XE

XG  > 16 + XD

XH  > 6 + XF

XFinish  >  XG

XFinish  >  XH

All variables > 0

Using the computer we find the time to complete the project is 35 weeks.

11-33.  An abbreviated PERT network digram for the Laurenster Corporation is as follows:

Start

A	3

B	6

C	5

D	4

E	7

F	7

G	5

H	5

I	5

J	2

K	4

L	3

Finish

The critical path is B-E-K with a mean project time of 17 and a standard deviation of 0.745.  Hence, the probability of completing the project in 16 weeks or less is the probability that Z is less than ((16 – 17)/0.745) = –1.341 for which the probability is approximately 0.0901.

11-34.  To get to 14 weeks and the bonus, the Laurenster Corporation would first have to crash the critical path from 17 weeks to 14 weeks by crashing both activity B and activity E to their fullest extent at a total cost of $1,800.  This will make path C-F-L a parallel critical path and it must be crashed as well.  This is done by crashing activity C by one week at a cost of $400.  Hence, the total cost of $2,200 is far less than the anticipated bonus and they should crash the project.

Solutions to Internet Homework Problems

11-35.

|  |  |  |  | Expected |  |
| --- | --- | --- | --- | --- | --- |
| Activity | a | m | b | Time | Variance |
| A | 3 | 6 | 8 | 5.83 | 0.69 |
| B | 2 | 4 | 4 | 3.67 | 0.11 |
| C | 1 | 2 | 3 | 2.00 | 0.11 |
| D | 6 | 7 | 8 | 7.00 | 0.11 |
| E | 2 | 4 | 6 | 4.00 | 0.44 |
| F | 6 | 10 | 14 | 10.00 | 1.78 |
| G | 1 | 2 | 4 | 2.17 | 0.25 |
| H | 3 | 6 | 9 | 6.00 | 1.00 |
| I | 10 | 11 | 12 | 11.00 | 0.11 |
| J | 14 | 16 | 20 | 16.33 | 1.00 |
| K | 2 | 8 | 10 | 7.33 | 1.78 |

11-36.  A network for the project is shown in the figure.

|  |  |  |  |  |  | Critical |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | ES | EF | LS | LF | Slack | Path |
| A | 0 | 5.83 | 7.17 | 13.00 | 7.17 | No |
| B | 0 | 3.67 | 5.33 | 9.00 | 5.33 | No |
| C | 0 | 2.00 | 0 | 2.00 | 0 | Yes |
| D | 2.00 | 9.00 | 2.00 | 9.00 | 0 | Yes |
| E | 9.00 | 13.00 | 9.00 | 13.00 | 0 | Yes |
| F | 13.00 | 23.00 | 13.00 | 23.00 | 0 | Yes |
| G | 13.00 | 15.17 | 15.83 | 18.00 | 2.83 | No |
| H | 23.00 | 29.00 | 23.00 | 29.00 | 0 | Yes |
| I | 15.17 | 26.17 | 18.00 | 29.00 | 2.83 | No |
| J | 2.00 | 18.33 | 20.00 | 36.33 | 18.00 | No |
| K | 29.00 | 36.33 | 29.00 | 36.33 | 0 | Yes |

The critical path is C–D–E–F–H–K. Project completion time is 36.33.

Figure for Problem 11-36

<NOXMLTAGINDOC> <DOCPAGE NUM="202"> <ART FILE="UN13_012_0136036287.EPS" W="362pt" H="169pt" XS="100%" YS="99.998%"/> </DOCPAGE> </NOXMLTAGINDOC>

11-37.  For the project, expected time = 36.33.

Vt = 0.11 + 0.11 + 0.44 + 1.78 + 1.00 + 1.78 = 5.22

Standard deviation = 2.28.

Probability of finishing project in less than 40 days:

<ART FILE="13_32eq01.EPS" W="85.385pt" H="26.115pt" XS="100%" YS="100%"/>

<ART FILE="13_32eq02.EPS" W="80.273pt" H="9.617pt" XS="100%" YS="100%"/>

11-38.  Before we can determine how long it will take team A to complete its programming assignment, we must develop a PERT diagram. The network showing the activities and node numbers is contained at the end of the solution for this particular problem. Once this network has been constructed, activities, and time estimates can be entered into the computer program. The first result from the computer program is a summarization of the expected time and variance for each activity. This information is shown in the table.

| <NOXMLTAGINDOC><DOCPAGE NUM="203"></DOCPAGE></NOXMLTAGINDOC>Activity | Time | Variance | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 (A) | 4.00 | 0.111 | 0.00 | 4.00 | 0.00 | 4.00 | 0.00* |
| 2 (B) | 5.17 | 0.250 | 4.00 | 9.17 | 6.00 | 11.17 | 2.00 |
| 3 (C) | 7.83 | 0.250 | 4.00 | 11.83 | 4.00 | 11.83 | 0.00* |
| 4 (D) | 3.17 | 0.250 | 4.00 | 7.17 | 6.67 | 9.83 | 2.67 |
| 5 (E) | 7.17 | 0.250 | 4.00 | 11.17 | 6.83 | 14.00 | 2.83 |
| 6 (F) | 4.00 | 0.111 | 4.00 | 8.00 | 6.17 | 10.17 | 2.17 |
| 7 (G) | 3.83 | 0.250 | 8.00 | 11.83 | 10.17 | 14.00 | 2.17 |
| 8 (H) | 4.17 | 0.250 | 7.17 | 11.33 | 9.83 | 14.00 | 2.67 |
| 9 (I) | 2.17 | 0.250 | 11.83 | 14.00 | 11.83 | 14.00 | 0.00* |
| 10 (J) | 2.83 | 0.250 | 9.17 | 12.00 | 11.17 | 14.00 | 2.00 |
| 11 (J) | 4.17 | 0.250 | 14.00 | 18.17 | 14.00 | 18.17 | 0.00* |
| 12 (K) | 5.83 | 0.250 | 18.17 | 24.00 | 18.17 | 24.00 | 0.00* |
| 13 (L) | 8.00 | 0.444 | 24.00 | 32.00 | 24.00 | 32.00 | 0.00* |
| 14 (M) | 4.17 | 0.250 | 32.00 | 36.17 | 32.00 | 36.17 | 0.00* |
| 15 (N) | 4.00 | 0.111 | 14.00 | 18.00 | 31.17 | 35.17 | 17.17 |
| 16 (N) | 4.00 | 0.444 | 18.00 | 22.00 | 35.17 | 39.17 | 17.17 |
| 17 (O) | 3.00 | 0.111 | 36.17 | 39.17 | 36.17 | 39.17 | 0.00* |
| 18 (P) | 4.83 | 0.250 | 39.17 | 44.00 | 39.17 | 44.00 | 0.00* |

*Indicates critical path activity.

Figure for Problem 11-38

<NOXMLTAGINDOC> <DOCPAGE NUM="203"> <ART FILE="UN13_013_0136036287.EPS" W="504pt" H="115.5pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

The expected project completion time is 44 weeks, and the variance is 2.167.

As can be seen in the table, the critical path for this particular problem includes activities 1, 3, 9, 11, 12, 13, 14, 17, and 18. The solution, however, is not complete. Software Development Specialist (SDS) is not sure about the time estimates for activity 5. As indicated in the problem, these time estimates might be as high as 12, 14, and 15 weeks for the optimistic, most likely, and pessimistic times. Now, we must find out what impact this possible increase in expected times would have on the network. Fortunately, our computer program has a convenient rerun capability. We are able to go back to the original data, modify the time estimates for these activities, and resolve the problem. Doing this will result in an expected project completion time of 47.83 weeks. The variance of the project is approximately 1.92 weeks. Will this change the critical path? The answer is yes. The critical path now includes activities 1, 5, 11, 12, 13, 14, 17, and 18. Activity 5 now lies along the critical path. The earliest start, earliest finish, latest start, latest finish, and slack times for all activities with the new time estimate  for activity 5 of 13.83 is shown in the table:

|  | Activity Time |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity |  |  |  |  |  |
|  | ES | EF | LS | LF | Slack |
| 1 | 0.00 | 4.00 | 0.00 | 4.00 | 0.00* |
| 2 | 4.00 | 9.17 | 9.83 | 15.00 | 5.83 |
| 3 | 4.00 | 11.83 | 7.83 | 15.67 | 3.83 |
| 4 | 4.00 | 7.17 | 10.50 | 13.67 | 6.50 |
| 5 | 4.00 | 17.83 | 4.00 | 17.83 | 0.00* |
| 6 | 4.00 | 8.00 | 10.00 | 14.00 | 6.00 |
| 7 | 8.00 | 11.83 | 14.00 | 17.83 | 6.00 |
| 8 | 7.17 | 11.33 | 13.67 | 17.83 | 6.50 |
| 9 | 11.83 | 14.00 | 15.67 | 17.83 | 3.83 |
| 10 | 9.17 | 12.00 | 15.00 | 17.83 | 5.83 |
| 11 | 17.83 | 22.00 | 17.83 | 22.00 | 0.00* |
| 12 | 22.00 | 27.83 | 22.00 | 27.83 | 0.00* |
| 13 | 27.83 | 35.83 | 27.83 | 35.83 | 0.00* |
| 14 | 35.83 | 40.00 | 35.83 | 40.00 | 0.00* |
| 15 | 17.83 | 21.83 | 35.00 | 39.00 | 17.17 |
| 16 | 21.83 | 25.83 | 39.00 | 43.00 | 17.17 |
| 17 | 40.00 | 43.00 | 40.00 | 43.00 | 0.00* |
| 18 | 43.00 | 47.83 | 43.00 | 47.83 | 0.00* |

*Indicates critical path activity.

11-39  a.  The first step for Jim Sager is to summarize the time estimates for each of the activities, and compute the expected time and the standard variance for each activity.   These are shown in the following table.

| Activity | Optimistic | Likely | Pessimistic | Time | Variance |
| --- | --- | --- | --- | --- | --- |
| 1(A) | 2 | 3 | 4 | 3 | 0.111 |
| 2(B) | 5 | 6 | 8 | 6.167 | 0.25 |
| 3(C) | 1 | 1 | 2 | 1.167 | 0.028 |
| 4(D) | 8 | 9 | 11 | 9.167 | 0.25 |
| 5(E) | 1 | 1 | 4 | 1.5 | 0.25 |
| 6(F) | 3 | 3 | 4 | 3.167 | 0.028 |
| 7(G) | 1 | 2 | 2 | 1.833 | 0.028 |
| 8(H) | 5 | 5 | 6 | 5.167 | 0.028 |
| 9(I) | 9 | 10 | 11 | 10 | 0.111 |
| 10(J) | 1 | 2 | 2 | 1.833 | 0.028 |
| 11(K) | 2 | 2 | 3 | 2.167 | 0.028 |
| 12(L) | 3 | 4 | 6 | 4.167 | 0.25 |
| 13(M) | 2 | 2 | 4 | 2.333 | 0.111 |
| 14(N) | 8 | 9 | 11 | 9.167 | 0.25 |
| 15(O) | 1 | 1 | 3 | 1.333 | 0.111 |
| 16(P) | 4 | 4 | 8 | 4.667 | 0.444 |
| 17(Q) | 6 | 6 | 7 | 6.167 | 0.028 |
| 18(R) | 1 | 2 | 4 | 2.167 | 0.25 |
| 19(S) | 6 | 6 | 7 | 6.167 | 0.028 |
| 20(T) | 3 | 3 | 4 | 3.167 | 0.028 |
| 21(U) | 1 | 2 | 3 | 2 | 0.111 |
| 22(V) | 9 | 10 | 11 | 10 | 0.111 |
| 23(W) | 2 | 4 | 5 | 3.833 | 0.25 |

Earliest and latest start and finish times (ES, EF, LS, and LF)  and slack times are then computed for each activity. This is shown in the table.

| <NOXMLTAGINDOC><DOCPAGE NUM="203"></DOCPAGE></NOXMLTAGINDOC>Activity | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 3 | 15.5 | 18.5 | 15.5 |
| B | 0 | 6.167 | 12.667 | 18.833 | 12.667 |
| C | 0 | 1.167 | 32 | 33.167 | 32 |
| D | 0 | 9.167 | 0 | 9.167 | 0 |
| E | 3 | 4.5 | 18.5 | 20 | 15.5 |
| F | 6.167 | 9.333 | 18.833 | 22 | 12.667 |
| G | 6.167 | 8 | 22 | 23.833 | 15.833 |
| H | 1.167 | 6.333 | 33.167 | 38.333 | 32 |
| I | 9.167 | 19.167 | 9.167 | 19.167 | 0 |
| J | 9.167 | 11 | 26 | 27.833 | 16.833 |
| K | 4.5 | 6.667 | 20 | 22.167 | 15.5 |
| L | 9.333 | 13.5 | 22 | 26.167 | 12.667 |
| M | 8 | 10.333 | 23.833 | 26.167 | 15.833 |
| N | 19.167 | 28.333 | 19.167 | 28.333 | 0 |
| O | 19.167 | 20.5 | 30 | 31.333 | 10.833 |
| P | 11 | 15.667 | 27.833 | 32.5 | 16.833 |
| Q | 6.667 | 12.833 | 22.167 | 28.333 | 15.5 |
| R | 13.5 | 15.667 | 26.167 | 28.333 | 12.667 |
| S | 28.333 | 34.5 | 28.333 | 34.5 | 0 |
| T | 20.5 | 23.667 | 31.333 | 34.5 | 10.833 |
| U | 15.667 | 17.667 | 32.5 | 34.5 | 16.833 |
| V | 15.667 | 25.667 | 28.333 | 38.333 | 12.667 |
| W | 34.5 | 38.333 | 34.5 | 38.333 | 0 |

The activities with no slack (D-I-N-S-W) are on the critical path.

The final network results are summarized:

Expected project length	= 38.3333

Variance of the critical path	= 0.8888

Standard deviation	= 0.9428

The project has an expected completion time of less than 40 weeks, although it is possible that the project could take longer.

11-40.  If activity D has already been completed, activity time for D is 0. The results are shown in the table. As you can see, activity D (4) is still on the critical path. The project completion time is now about 29 weeks.

<NOXMLTAGINDOC><DOCPAGE NUM="205"></DOCPAGE></NOXMLTAGINDOC>Table for Problem 11-40

| Activity | Mean | S.D. | Variance |
| --- | --- | --- | --- |
| 1(A) | 3.000 | 0.333 | 0.111 |
| 2(B) | 6.167 | 0.500 | 0.250 |
| 3(C) | 1.167 | 0.167 | 0.028 |
| 4(D)* | 0.000 | 0.000 | 0.000 |
| 5(E) | 1.500 | 0.500 | 0.250 |
| 6(F) | 3.167 | 0.167 | 0.028 |
| 7(G) | 1.833 | 0.167 | 0.028 |
| 8(H) | 5.167 | 0.167 | 0.028 |
| 9(I)* | 10.000 | 0.333 | 0.111 |
| 10(J) | 1.833 | 0.167 | 0.028 |
| 11(K) | 2.167 | 0.167 | 0.028 |
| 12(L) | 4.167 | 0.500 | 0.250 |
| 13(M) | 2.333 | 0.333 | 0.111 |
| 14(N)* | 9.167 | 0.500 | 0.250 |
| 15(O) | 1.333 | 0.333 | 0.111 |
| 16(P) | 4.667 | 0.667 | 0.444 |
| 17(Q) | 6.167 | 0.167 | 0.028 |
| 18(R) | 2.167 | 0.500 | 0.250 |
| 19(S)* | 6.167 | 0.167 | 0.028 |
| 20(T) | 3.167 | 0.167 | 0.028 |
| 21(U) | 2.000 | 0.333 | 0.111 |
| 22(V) | 10.000 | 0.333 | 0.111 |
| 23(W)* | 3.833 | 0.500 | 0.250 |

*Critical path activities.

Expected completion time is 29.167 weeks.

11-41.  The results of having both activity D (4) and I (9) completed are shown in the table. These activities are no longer on the critical path. The project completion time is now about 26 weeks.

| Activity | Mean | S.D. | Variance |
| --- | --- | --- | --- |
| 1(A) | 3.000 | 0.333 | 0.111 |
| 2(B) | 6.167 | 0.500 | 0.250 |
| 3(C) | 1.167 | 0.167 | 0.028 |
| 4(D) | 0.000 | 0.000 | 0.000 |
| 5(E) | 1.500 | 0.500 | 0.250 |
| 6(F) | 3.167 | 0.167 | 0.028 |
| 7(G) | 1.833 | 0.167 | 0.028 |
| 8(H) | 5.167 | 0.167 | 0.028 |
| 9(I) | 0.000 | 0.000 | 0.000 |
| 10(J) | 1.833 | 0.167 | 0.028 |
| 11(K) | 2.167 | 0.167 | 0.028 |
| 12(L) | 4.167 | 0.500 | 0.250 |
| 13(M) | 2.333 | 0.333 | 0.111 |
| 14(N) | 9.167 | 0.500 | 0.250 |
| 15(O) | 1.333 | 0.333 | 0.111 |
| 16(P) | 4.667 | 0.667 | 0.444 |
| 17(Q) | 6.167 | 0.167 | 0.028 |
| 18(R) | 2.167 | 0.500 | 0.250 |
| 19(S) | 6.167 | 0.167 | 0.028 |
| 20(T) | 3.167 | 0.167 | 0.028 |
| 21(U) | 2.000 | 0.333 | 0.111 |
| 22(V) | 10.000 | 0.333 | 0.111 |
| 23(W) | 3.833 | 0.500 | 0.250 |

Critical path activities: B–F–L–R–V

Expected completion time is 25.667 weeks.

11-42.  Changing the immediate predecessor activity will change the structure of the network. Fortunately, we can handle this situation. The results are shown in the table. Activity F (6) now goes from node 2 to node 7. Node 2 is the ending node for activity A (1). Thus activity F now has activity A as an immediate predecessor.

| Activity | Mean | S.D. | Variance |
| --- | --- | --- | --- |
| 1(A) | 3.000 | 0.333 | 0.111 |
| 2(B)* | 6.167 | 0.500 | 0.250 |
| 3(C) | 1.167 | 0.167 | 0.028 |
| 4(D) | 0.000 | 0.000 | 0.000 |
| 5(E) | 1.500 | 0.500 | 0.250 |
| 6(F)* | 3.167 | 0.167 | 0.028 |
| 7(G) | 1.833 | 0.167 | 0.028 |
| 8(H) | 5.167 | 0.167 | 0.028 |
| 9(I) | 0.000 | 0.000 | 0.000 |
| 10(J) | 1.833 | 0.167 | 0.028 |
| 11(K) | 2.167 | 0.167 | 0.028 |
| 12(L)* | 4.167 | 0.500 | 0.250 |
| 13(M) | 2.333 | 0.333 | 0.111 |
| 14(N) | 9.167 | 0.500 | 0.250 |
| 15(O) | 1.333 | 0.333 | 0.111 |
| 16(P) | 4.667 | 0.667 | 0.444 |
| 17(Q) | 6.167 | 0.167 | 0.028 |
| 18(R)* | 2.167 | 0.500 | 0.250 |
| 19(S) | 6.167 | 0.167 | 0.028 |
| 20(T) | 3.167 | 0.167 | 0.028 |
| 21(U) | 2.000 | 0.333 | 0.111 |
| 22(V)* | 10.000 | 0.333 | 0.111 |
| 23(W) | 3.833 | 0.500 | 0.250 |

*Critical path activities.

Expected completion time is 22.833 weeks.

Solutions to Southwestern University Stadium Construction Case

1.

Figure 1 Network Using Activity-On-Node Notation<NOXMLTAGINDOC> <DOCPAGE NUM="206"> <ART FILE="UN13_014_0136036287.EPS" W="328pt" H="134pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

The expected times (t) and the variance for each activity are shown in the table.

|  |  | Most |  | Activity |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Optimistic | Likely | Pessimistic | time | Standard |  |
| Activity | time | time | time | (t) | Deviation | Variance |
| A | 20 | 30 | 40 | 30 | 3.333333 | 11.11111 |
| B | 20 | 65 | 80 | 60 | 10 | 100 |
| C | 50 | 60 | 100 | 65 | 8.333333 | 69.44444 |
| D | 30 | 50 | 100 | 55 | 11.66667 | 136.1111 |
| E | 25 | 30 | 35 | 30 | 1.666667 | 2.777778 |
| F | 1 | 1 | 1 | 1 | 0 | 0 |
| G | 25 | 30 | 35 | 30 | 1.666667 | 2.777778 |
| H | 10 | 20 | 30 | 20 | 3.333333 | 11.11111 |
| I | 20 | 25 | 60 | 30 | 6.666667 | 44.44444 |
| J | 8 | 10 | 12 | 10 | 0.6666667 | 0.4444445 |
| K | 1 | 1 | 1 | 1 | 0 | 0 |
| L | 20 | 25 | 60 | 30 | 6.666667 | 44.44444 |

To find the critical path, the early start and finish times together with the latest times are used to find the slack as shown in the table. From this, the critical path is found.

|  | Activity | Early | Early | Late | Late |  | Standard |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | time | Start | Finish | Start | Finish | Slack | Deviation |
| A | 30 | 0 | 30 | 0 | 30 | 0 | 3.33333 |
| B | 60 | 30 | 90 | 60 | 120 | 30 | 10 |
| C | 65 | 30 | 95 | 30 | 95 | 0 | 8.333333 |
| D | 55 | 95 | 150 | 95 | 150 | 0 | 11.66667 |
| E | 30 | 90 | 120 | 120 | 150 | 30 | 1.666667 |
| F | 1 | 120 | 121 | 259 | 260 | 139 | 0 |
| G | 30 | 150 | 180 | 150 | 180 | 0 | 1.666667 |
| H | 20 | 180 | 200 | 180 | 200 | 0 | 3.333333 |
| I | 30 | 200 | 230 | 200 | 230 | 0 | 6.666667 |
| J | 10 | 200 | 210 | 219 | 229 | 19 | 0.6666667 |
| K | 1 | 210 | 211 | 229 | 230 | 19 | 0 |
| L | 20 | 230 | 260 | 230 | 260 | 0 | 6.666667 |

The project is expected to take 260 weeks. The critical path consists of activities A-C-D-G-H-I-L.

2.  To find the probabilities, we add the variances of the critical activities and find a project variance of 319.444. The standard deviation is 17.873. Letting X = project completion time,

<ART FILE="13_33eq01.EPS" W="211.333pt" H="25.714pt" XS="100%" YS="100%"/>

Thus, there is about 71% chance of finishing the project in 270 weeks.

3.  To get a completion time of 250 days, we crash activity A for 10 days at a cost of $15,000. This reduces the time to 250 days.

To get a completion time of 240 days, in addition to crashing A for 10 days, we crash activity D for 10 days at a cost of $19,000. The total cost of crashing is $34,000.

Solution to Family Planning Research Center of Nigeria Case

This case covers three aspects of project management:

1.  Critical path scheduling

2.  Crashing

3.  Personnel smoothing

The statement by Mr. Odaga that the project will take 94 days is a red herring. That is the sum of all the task times that would be the length of the project only if all of the tasks were done serially with none in parallel. Therefore, the assignment questions would be as follows:

Network formulation. Figure 1 shows a PERT formulation of a network based on the data on precedences and task (activity) times for each activity. The critical path is C–H–I–J–K of length 67. Table 1 shows the earliest start and finish times and the slacks for each activity, confirming this definition of the critical path.

Workforce smoothing. The case asks whether the effort can be carried out with the current staff of 10. Figure 2 shows the network with the staffing requirements. Table 2 shows a blank form that can be used to insert the staffing by activity and compute the daily staffing requirements. This form is used in Table 3 and shows the staffing requirement with each activity beginning on its earliest start date. There are five days on which there are requirements for more than 10 workers. Delaying of some of the activities with slack (activities D, E, F, and G) results in the feasible schedule in Table 4.

Table 1

Latest and earliest starting times and slack

| Activity | LS | ES | Slack |
| --- | --- | --- | --- |
| A. Identify faculty | 8 | 0 | 8 |
| B. Arrange transport | 12 | 0 | 12 |
| C. Identify material | 0 | 0 | 0 |
| D. Arrange accommodations | 19 | 5 | 14 |
| E. Identify team | 13 | 5 | 8 |
| F. Bring in team | 20 | 12 | 8 |
| G. Transport faculty | 19 | 7 | 12 |
| H. Print materials | 5 | 5 | 0 |
| I. Deliver materials | 15 | 15 | 0 |
| J. Train | 22 | 22 | 0 |
| K. Fieldwork | 37 | 37 | 0 |

<NOXMLTAGINDOC><DOCPAGE NUM="209"></DOCPAGE></NOXMLTAGINDOC>Figure 1 Network for Family Planning Research<NOXMLTAGINDOC> <DOCPAGE NUM="209"> <ART FILE="UN13_015_0136036287.EPS" W="356pt" H="148pt" XS="100%" YS="99.998%"/> </DOCPAGE> </NOXMLTAGINDOC>

Staff 2

Staff 6

Figure 2 Staffing Network for Family Planning Research<NOXMLTAGINDOC> <DOCPAGE NUM="209"> <ART FILE="UN13_016_0136036287.EPS" W="352pt" H="144.5pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

Table 2

Blank Staffing Chart

|  | Day |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 3

Chart Showing Each Day’s Manpower Requirements if All Activities Are Started at ES

|  | Day |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| A | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| H |  |  |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  |  |  |  |  |
| I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 |
| Total | 7 | 7 | 7 | 7 | 7 | 14 | 14 | 13 | 12 | 12 | 10 | 10 | 7 | 7 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |

Table 4

Minimum Number of Personnel Needed for 22-Day Completion Time

|  | Day |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| A | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |
| E |  |  |  |  |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |
| H |  |  |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  |  |  |  |
| I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 |
| Total | 7 | 7 | 7 | 7 | 7 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 6 | 5 | 3 | 3 | 3 | 3 |

Table 5

Crashing Procedure

| Step | Length (Days) | Total Cost |
| --- | --- | --- |
| 1. Original network | 67 | $25,400 |
| 2. Crash C 5–3 | 65 | 25,500 |
| 3. Crash I 7–2 | 60 | 25,900 |
| 4. Crash H 10–9 | 59 | 26,100 |
| Second critical path emerges |  |  |
| 5. Crash A 5–2 and H 9–6 | 56 | 27,000 |
| 6. Crash H 6–5 and E 7–6 | 55 | 27,350 |
| Third critical path emerges |  |  |
| 7. Crash J 15–10 | 50 | 29,350 |
| 8. Crash K 30–20 | 40 | 33,350 |

Crashing the schedule. Since the objective is a 60-rather than a 67-day schedule, the team must investigate the possibilities of crashing activities on the critical path(s) to reduce project duration using the data exhibited in the case. Table 5 shows the sequence of crashing to get to various project lengths. Getting to 60 days is relatively easy and relatively cheap. Activity C is reduced by 2 days at a cost of $50 per day. The next cheapest alternative is activity I, which can be cut 5 days, for a total cost of $400. Therefore, Dr. Watage needs to request $500 from the Pathminder Foundation to crash the project to the 60-day duration. The instructor can also use these data to indicate to the students how further crashing would generate multiple parallel paths and necessitate use of a heuristic rule to select the activities to be cut further to shorten the network.

Warning: Take up the workforce smoothing before you take up crashing. After you have smoothed out the labor and then crashed the project by 7 days, the network A through I will go from 22 to 15 days and the project will be infeasible with the 10 personnel at hand. Don’t try to redo the smoothing. Just indicate to the students that the extra money used for crashing might have been used to hire temporary help to overcome this constraint. Some students may try to do the crashing and then the smoothing and become stymied by the resulting infeasibility.

Solution to Internet CaseS

SOLUTION TO ALPHA BETA GAMMA RECORD CASE

1.  The PERT diagram is shown. The activity times are the averages calculated from the formula

t = (a + 4m + b)/6

where a is the minimum, m is the most likely, and b is the maximum activity time. These are shown in Table 1 for those activities whose times might vary. Also shown are the variances of these activity times calculated from v = [(b – a)/6]2. The activities not shown in Table 1 are deterministic with variance zero.

<NOXMLTAGINDOC><DOCPAGE NUM="213"></DOCPAGE></NOXMLTAGINDOC>Table 1

Mean and Variance for Variable Length Activities

| Activity | Mean | Variance |
| --- | --- | --- |
| A | 2 | 0.1111 |
| B | 2 | 0.4444 |
| C | 1 | 0.0278 |
| D | 1 | 0.1111 |
| H | 1 | 0.0069 |
| I | 3 | 0.4444 |
| J | 3 | 0.4444 |
| L | 2 | 0.1111 |
| Q | 1 | 0.0278 |

PERT Networks: Thrift Print and Kwik Print showing expected values

A.  Thrift Print

Total Completion time = 31.5 days<NOXMLTAGINDOC> <DOCPAGE NUM="213"> <ART FILE="UN13_18a_0136036287.EPS" W="358pt" H="72pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

B.  Kwik Print

Total Completion time = 31 days<NOXMLTAGINDOC> <DOCPAGE NUM="213"> <ART FILE="UN13_18b_0136036287.EPS" W="347.1pt" H="83pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

2.  The critical path has an expected length of 31.5 with variance of 0.6944. This yields a standard normal variable

<ART FILE="13_33eq05.EPS" W="116.571pt" H="14.083pt" XS="100%" YS="100%"/>

Virtually all of the issues will be on time.

3.  The second solution critical path has an expected length of 31.0 with variance 0.6944. This yields a standard normal value of 4.8; virtually all of the issues will be on time.

4.  This question is behavioral in nature and can be answered in a multitude of ways. Factors in this analysis could include the alum’s status with the fraternity, the possibility of a reduction in printing costs from Thrift Print and the possibility of reducing the number of issues of the Record. Depending on the factors discussed, many system-wide effects could be felt.

SOLUTION TO BAY COMMUNITY HOSPITAL CASE

1. The earliest and latest times are shown in the table below.  The minimum time to complete the project base on the original numbers is 10.  The critical path is E-F.

| Activity | Activity time | Early Start | Early Finish | Late Start | Late Finish | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 2 | 0 | 2 | 3 | 5 | 3 |
| B | 4 | 0 | 4 | 1 | 5 | 1 |
| C | 3 | 4 | 7 | 5 | 8 | 1 |
| D | 4 | 4 | 8 | 6 | 10 | 2 |
| E | 8 | 0 | 8 | 0 | 8 | 0 |
| F | 2 | 8 | 10 | 8 | 10 | 0 |

2.  If activity E on the critical path is reduced by one week using express truck, the completion time becomes 9 weeks with two critical paths: E, F and B, C, F. The completion time can be reduced to 8 weeks by resorting to air shipment in activity e and using overtime in activity C.

3.  The cost of air shipment ($750) and overtime ($600) would increase the cost by $1,350. However, $300 could be saved by allowing activity a (not on any of the critical paths) to take 3 weeks yielding a net cost increase of $1,050.

SOLUTION TO CRANSTON CONSTRUCTION COMPANY CASE

This case was based on a real construction project.  The activities list for the Humanities Building at the University of Northern Mississippi is shown in Table 1 that follows. The network graph is shown in Figure 1.  The project involved very high costs and was directly amenable to critical path methods.  The project extended over a period of approximately one year. In a project of this length, weekly reports by the contractor would be necessary for controlling the project.

The critical path for this project had a time of 379 days, which would exceed the 370 day target.  The critical activities  are the ones with zero slack.  If information about crashing were available, one or more of the activities on the critical path would have to be crashed.

Table 1.  Cranston Construction Times

| Activity | Activity time | Early Start | Early Finish | Late Start | Late Finish | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 28 | 0 | 28 | 0 | 28 | 0 |
| B | 21 | 0 | 21 | 7 | 28 | 7 |
| C | 7 | 0 | 7 | 21 | 28 | 21 |
| D | 11 | 28 | 39 | 28 | 39 | 0 |
| E | 11 | 28 | 39 | 28 | 39 | 0 |
| F | 10 | 39 | 49 | 39 | 49 | 0 |
| G | 21 | 49 | 70 | 49 | 70 | 0 |
| H | 35 | 70 | 105 | 70 | 105 | 0 |
| I | 12 | 105 | 117 | 105 | 117 | 0 |
| J | 23 | 117 | 140 | 117 | 140 | 0 |
| K | 37 | 140 | 177 | 140 | 177 | 0 |
| L | 14 | 177 | 191 | 177 | 191 | 0 |
| M | 23 | 191 | 214 | 191 | 214 | 0 |
| N | 37 | 214 | 251 | 214 | 251 | 0 |
| O | 14 | 251 | 265 | 258 | 272 | 7 |
| P | 21 | 251 | 272 | 251 | 272 | 0 |
| Q | 21 | 251 | 272 | 251 | 272 | 0 |
| R | 21 | 177 | 198 | 342 | 363 | 165 |
| S | 21 | 272 | 293 | 293 | 314 | 21 |
| T | 21 | 272 | 293 | 293 | 314 | 21 |
| U | 42 | 272 | 314 | 272 | 314 | 0 |
| V | 42 | 314 | 356 | 314 | 356 | 0 |
| W | 42 | 293 | 335 | 314 | 356 | 21 |
| X | 28 | 293 | 321 | 349 | 377 | 56 |
| Y | 21 | 356 | 377 | 356 | 377 | 0 |
| Z | 2 | 377 | 379 | 377 | 379 | 0 |
| AA | 14 | 198 | 212 | 363 | 377 | 165 |
| BB | 35 | 105 | 140 | 328 | 363 | 223 |
| CC | 14 | 140 | 154 | 363 | 377 | 223 |
| DD | 14 | 105 | 119 | 188 | 202 | 83 |
| EE | 35 | 119 | 154 | 202 | 237 | 83 |
| FF | 21 | 105 | 126 | 356 | 377 | 251 |
| GG | 35 | 105 | 140 | 342 | 377 | 237 |
| HH | 14 | 177 | 191 | 223 | 237 | 46 |
| II | 35 | 191 | 226 | 237 | 272 | 46 |

Figure 1 Network Graph for Cranston Case<NOXMLTAGINDOC> <DOCPAGE NUM="212"> <ART FILE="UN13_017_0136036287.EPS" W="389pt" H="151pt" XS="100%" YS="100%"/> </DOCPAGE> </NOXMLTAGINDOC>

Solution to Haygood Brothers Construction Company Case

Using the formulas to calculate the expected times and variances for the activities yields the results in the following table.

| Activity | a | m | b | t | Variance |
| --- | --- | --- | --- | --- | --- |
| A | 4 | 5 | 6 | 5 | 0.11 |
| B | 2 | 5 | 8 | 5 | 1 |
| C | 5 | 7 | 9 | 7 | 0.44 |
| D | 4 | 5 | 6 | 5 | 0.11 |
| E | 2 | 4 | 6 | 4 | 0.44 |
| F | 3 | 5 | 9 | 5.33 | 1 |
| G | 4 | 5 | 6 | 5 | 0.11 |
| H | 3 | 4 | 7 | 4.33 | 0.44 |
| I | 5 | 7 | 9 | 7 | 0.44 |
| J | 10 | 11 | 12 | 11 | 0.11 |
| K | 7 | 8 | 9 | 8 | 0.11 |
| L | 4 | 6 | 8 | 6 | 0.44 |
| M | 5 | 7 | 9 | 7 | 0.44 |
| N | 4 | 5 | 10 | 5.67 | 1 |
| O | 5 | 6 | 7 | 6 | 0.11 |
| P | 2 | 3 | 4 | 3 | 0.11 |

The earliest, latest and slack times are shown here.

| Activity | t | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 5 | 0 | 5 | 0 | 5 | 0 |
| B | 5 | 5 | 10 | 5 | 10 | 0 |
| C | 7 | 10 | 17 | 10 | 17 | 0 |
| D | 5 | 10 | 15 | 23 | 28 | 13 |
| E | 4 | 17 | 21 | 17 | 21 | 0 |
| F | 5.33 | 21 | 26.33 | 33.67 | 39 | 12.67 |
| G | 5 | 21 | 26 | 34 | 39 | 13 |
| H | 4.33 | 21 | 25.33 | 34.67 | 39 | 13.67 |
| I | 7 | 21 | 28 | 21 | 28 | 0 |
| J | 11 | 28 | 39 | 28 | 39 | 0 |
| K | 8 | 39 | 47 | 44.33 | 52.33 | 5.33 |
| L | 6 | 39 | 45 | 39 | 45 | 0 |
| M | 7 | 45 | 52 | 45 | 52 | 0 |
| N | 5.67 | 47 | 52.67 | 52.33 | 58 | 5.33 |
| O | 6 | 52 | 58 | 52 | 58 | 0 |
| P | 3 | 58 | 61 | 58 | 61 | 0 |

The critical path is A–B–C–E–I–J–L–M–O–P (61 days).  This path has a variance of 3.667 and a standard deviation of 1.92.

A delay in the completion of an event on the critical path will delay the entire project by an equal amount of time.  For a project completion time (X) of 60, we find

<ART FILE="13_33eq02.EPS" W="112.571pt" H="26.857pt" XS="100%" YS="100%"/>

So there is about a 30% chance of finishing in 60 days or less.

<ART FILE="13_33eq03.EPS" W="61.714pt" H="13pt" XS="100%" YS="100%"/>

SOLUTION TO SHALE OIL COMPANY CASE STUDY

1.  Determine the expected shutdown time, and the probability the shutdown will be completed one week earlier.

2.  What are the probabilities that Shale finishes the maintenance project one day, two days, three days, four days, five days, or six days earlier?

From the precedence data supplied in the problem, we can develop the following network:

The following table indicates the expected times, variances, and slacks needed to complete the rest of the problem.

| <NOXMLTAGINDOC><DOCPAGE NUM="215"></DOCPAGE></NOXMLTAGINDOC>Task |  | Most |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Optimistic | likely | Pessimistic | E(t) |  | ES | EF | LS | LF | Slack |
| 1 | 1 | 2 | 2.5 | 1.92 | 0.25 | 0 | 1.92 | 0 | 1.92 | 0 |
| 2 | 1.5 | 2 | 2.5 | 2 | 0.17 | 1.92 | 3.92 | 1.92 | 3.92 | 0 |
| 3 | 2 | 3 | 4 | 3 | 0.33 | 3.92 | 6.92 | 3.92 | 6.92 | 0 |
| 4 | 1 | 2 | 3 | 2 | 0.33 | 3.92 | 5.92 | 22.5 | 24.5 | 18.58 |
| 5 | 1 | 2 | 4 | 2.17 | 0.5 | 3.92 | 6.08 | 10.25 | 12.42 | 6.333 |
| 6 | 2 | 2.5 | 3 | 2.5 | 0.17 | 3.92 | 6.42 | 13.42 | 15.92 | 10 |
| 7 | 2 | 4 | 5 | 3.83 | 0.5 | 3.92 | 7.75 | 29.58 | 33.42 | 25.67 |
| 8 | 1 | 2 | 3 | 2 | 0.33 | 6.92 | 8.92 | 6.92 | 8.92 | 0 |
| 9 | 1 | 1.5 | 2 | 1.5 | 0.17 | 5.92 | 7.42 | 26.67 | 28.17 | 20.75 |
| 10 | 1 | 1.5 | 2 | 1.5 | 0.17 | 5.92 | 7.42 | 24.5 | 26 | 18.58 |
| 11 | 2 | 2.5 | 3 | 2.5 | 0.17 | 6.08 | 8.58 | 19.92 | 22.42 | 13.83 |
| 12 | 15 | 20 | 30 | 20.83 | 2.5 | 6.08 | 26.92 | 12.42 | 33.25 | 6.33 |
| 13 | 1 | 1.5 | 2 | 1.5 | 0.17 | 6.42 | 7.92 | 15.92 | 17.42 | 10 |
| 14 | 3 | 5 | 8 | 5.17 | 0.83 | 6.42 | 11.58 | 28.08 | 33.25 | 21.67 |
| 15 | 3 | 8 | 15 | 8.33 | 2 | 7.75 | 16.08 | 33.42 | 41.75 | 25.67 |
| 16 | 14 | 21 | 28 | 21 | 2.33 | 8.92 | 29.92 | 8.92 | 29.92 | 0 |
| 17 | 1 | 5 | 10 | 5.17 | 1.5 | 7.42 | 12.58 | 28.17 | 33.33 | 20.75 |
| 18 | 2 | 5 | 10 | 5.33 | 1.33 | 7.42 | 12.75 | 26 | 31.33 | 18.58 |
| 19 | 5 | 10 | 20 | 10.83 | 2.5 | 8.58 | 19.42 | 22.42 | 33.25 | 13.83 |
| 20 | 10 | 15 | 25 | 15.83 | 2.5 | 7.92 | 23.75 | 17.42 | 33.25 | 10 |
| 21 | 4 | 5 | 8 | 5.33 | 0.67 | 29.92 | 35.25 | 29.92 | 35.25 | 0 |
| 22 | 1 | 2 | 3 | 2 | 0.33 | 12.75 | 14.75 | 31.33 | 33.33 | 18.58 |
| 23 | 1 | 2 | 2.5 | 1.92 | 0.25 | 14.75 | 16.67 | 33.33 | 35.25 | 18.58 |
| 24 | 1 | 2 | 3 | 2 | 0.33 | 26.92 | 28.92 | 33.25 | 35.25 | 6.33 |
| 25 | 1 | 2 | 3 | 2 | 0.33 | 23.75 | 25.75 | 33.25 | 35.25 | 9.5 |
| 26 | 2 | 4 | 6 | 4 | 0.67 | 16.08 | 20.08 | 41.75 | 45.75 | 25.67 |
| 27 | 1.5 | 2 | 2.5 | 2 | 0.17 | 35.25 | 37.25 | 35.25 | 37.25 | 0 |
| 28 | 1 | 3 | 5 | 3 | 0.67 | 37.25 | 40.25 | 37.25 | 40.25 | 0 |
| 29 | 3 | 5 | 10 | 5.5 | 1.17 | 40.25 | 45.75 | 40.25 | 45.75 | 0 |

From the table, we can see that the expected shutdown time is 45.75 or 46 days. There are 9 activities on the critical path.

| Activities on the critical path |  |  |
| --- | --- | --- |
| Task |  | 2 |
| 1 | 0.25 | 0.0625 |
| 2 | 0.17 | 0.0289 |
| 3 | 0.33 | 0.1089 |
| 8 | 0.33 | 0.1089 |
| 16 | 2.33 | 5.4289 |
| 21 | 0.67 | 0.4489 |
| 27 | 0.17 | 0.0289 |
| 28 | 0.67 | 0.4489 |
| 29 | 1.17 | 1.3689 |
| Variance for critical path: |  | 8.0337 |

Therefore,  = 2.834.

As an approximation, we can use the customary equation for the Normal Distribution:

<ART FILE="13_33eq06.EPS" W="76.693pt" H="24pt" XS="100%" YS="100%"/>

(Note: This might be a good time to discuss the difference between a continuous and a discrete probability distribution, and the appropriate procedure for using a continuous distribution as an approximation to a discrete, if you have not already done so.)

| Finish Time | Z | Probability |
| --- | --- | --- |
| One day early | –0.353 | 36.3% |
| Two days early | –0.706 | 24.0 |
| Three days early | –1.058 | 14.5 |
| Four days early | –1.411 | 7.9 |
| Five days early | –1.764 | 3.9* |
| Six days early | –2.117 | 1.7 |
| Seven days early | –2.470 | 0.7 |

*The appropriate procedure for using the Normal distribution gives 3.0%—roughly a 30% difference.

There is, by the approximate procedure used, a 3.9% probability of finishing five days or one week early.

3.  Shale Oil is considering increasing the budget to shorten the shutdown. How do you suggest the company proceed?

In order to shorten the shutdown, Shale Oil would have to determine the costs of decreasing the activities on the critical path. This is the vessel and column branch of the network which is typically the longest section in a shutdown. The cost of reducing activity time by one time unit for each activity in this branch would have to be calculated. The activity with the lowest of these costs could then be acted upon. Perhaps the repairs to the vessels and columns could be expedited with workers from some of the other branches with high slack time. However, delivery on materials could be an overriding factor.

<NOXMLTAGINDOC> <DOCPAGE NUM="190"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="192"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="194"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="196"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="198"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="200"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="202"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="204"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="206"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC><DOCPAGE NUM="207"></DOCPAGE></NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="208"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="210"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC><DOCPAGE NUM="211"></DOCPAGE></NOXMLTAGINDOC><NOXMLTAGINDOC> <DOCPAGE NUM="212"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="214"> </DOCPAGE> </NOXMLTAGINDOC>

<NOXMLTAGINDOC> <DOCPAGE NUM="216"> </DOCPAGE> </NOXMLTAGINDOC>